## Start
ABOUT THIS TEMPLATE
Use this template to create a Weekly Attendance Report.
Fill in Room Name or number, Time and Period, Teacher, Course names, and Week start date.
Enter Student Names and Y for yes in Attendance table to mark student as Present, Tardy, Unexcused, or Excused for corresponding day.
Note:
Additional instructions have been provided in column A in WEEKLY ATTENDANCE REPORT worksheet. This text has been intentionally hidden. To remove text, select column A, then select DELETE. To unhide text, select column A, then change font color.
To learn more about table, press SHIFT and then F10 within the table, select the TABLE option, and then select ALTERNATIVE TEXT.

## Weekly Attendance Report
Create a Weekly Attendance Report in this worksheet. Title of the worksheet is in cell at right. Helpful instructions on how to use this worksheet are in cells in this column. Arrow down to get started. | RateIT | TIMELINE
Enter Room name or number in cell C2. Weekdays are in cells F2 through V2. | TASK |  | Week 1 |  |  |  | Week 2 |  |  |  | Week 3 | [7 empty] | Week 4 |  |  |  | Week 5
Enter details in Attendance table starting in cell E3. |  | ASSIGNED TO | S | M | T | W | TH | S2 | M2 | T2 | W2 | TH2 | S3 | M3 | T3 | W3 | TH3 | S4 | M4 | T4 | W4 | TH4 | S5 | M5 | T5 | W5 | TH5
Enter Period and Time in cell C4. Next instruction is in cell A6. | A: Requirement Analysis
| A.1:Draw the context | NISHO
Legends are defined in cells C12 through C15. | A.2:Develop ptototypes | DIP
| A.3:Model the requirement | DIP
| A.4: Finalise the requirements | NISHO
B.System Design
| B.1:Use case diagram | DIP
| B.2:Activity diagram | NISHO
| B.3:Mock design | DIP
| B.4:Class diagram | NISHO
C:Development
| C.1:Interface design | DIP,NISHO
| C.2:Code module 1 | DIP
| C.3:Code module 2 | NISHO
| C.4:Class define | DIP,NISHO
D.Testing
| D.1:Functional testing | DIP,NISHO
| D.2:Non-functional testing | NISHO
| D.3:Security testing | DIP
| D.4:Product quality testing | NISHO
E:Maintenance
| E.1:Bug fixing | DIP,NISHO
| E.2:New functionality adding | NISHO